## Planilha1
SQLITE | PRIMAVERA | SQLITE | PRIMAVERA | obs |  | SQLITE | VALOR SQLITE | PRIMAVERA | VALOR PRIMAVERA |  |  |  | SQLITE | VALOR SQLITE | PRIMAVERA | VALOR PRIMAVERA |  | SQLITE | VALOR SQLITE | PRIMAVERA | VALOR PRIMAVERA | SQLITE | VALOR SQLITE | PRIMAVERA | VALOR PRIMAVERA | SQLITE | VALOR SQLITE | PRIMAVERA | VALOR PRIMAVERA | SQLITE | VALOR SQLITE | PRIMAVERA | VALOR PRIMAVERA
PROJECT | JANELA PROJECT | PROJWBS | JANELA WBS |  |  | TASK |  | ATIVIDADES |  |  |  |  | TASKRSRC |  | ATIV. C/ REC. |  |  | TASKFIN |  | ATIVIDADES |  | ACTVTYPE |  | ATIVIDADES |  | TASKPRED |  | ATIVIDADES |  | RSRC |  | ATIVIDADES
PROJ_ID | NÃO TEM | PROJ_ID | NÃO TEM |  |  | PROJ_ID | 4366 | NÃO TEM |  |  |  |  | TASKRSRC_ID | 73056 | NÃO TEM |  |  | FIN_DATES_ID | 206 | NÃO TEM |  | ACTV_CODE_TYPE_ID | 149 |  |  | TASK_PRED_ID | 32659 | não tem
PROJ_SHORT_NAME | PROJECT ID | WBS_ID | NÃO TEM |  |  | WBS_ID | 24643 | NÃO TEM |  |  |  |  | TASK_ID | 95493 | NÃO TEM |  |  | TASK_ID | 95493 | NÃO TEM |  | ACTV_CODE_TYPE | Phase |  |  | TASK_ID | 95493
LAST_RECALL_DATE | DATA DATE | WBS_SHORT_NAME | PROJECT ID |  |  | TASK_ID | 95493 | NÃO TEM |  |  |  |  | PROJ_ID | 4366 | NÃO TEM |  |  | PROJ_ID | 4366 | NÃO TEM |  | PROJ_ID |  |  |  | PRED_TASK_ID | 95492
PLAN_START_DATE | START | WBS_NAME | PROJECT NAME e WBS NAME | N = Nome da WBS |  | TASK_CODE | EC1100 | Activity ID |  |  |  |  | ROLE_ID | 1175 | NÃO TEM |  |  | ACT_WORK_QTY | 170 |  |  | ACTV_CODE_TYPE_SCOPE | AS_Global |  |  | PROJ_ID | 4366
SCD_END_DATE | FINISH | PROJ_NODE_FLAG | Y |  |  | TASK_NAME | SITE PREPARATION | Activity Name |  |  |  |  | ACCT_ID | 690 | NÃO TEM |  |  | ACT_WORK_COST | 11900 | [6 empty] | PRED_PROJ_ID | 4366
DEF_DURATION_TYPE | DT_FixedDUR2 |  |  |  |  | RSRC_ID | 6600 | NÃO TEM |  |  |  |  | REMAIL_QTY | 0 |  |  |  | ACT_EQUIP_QTY | 0 | [6 empty] | PRED_TYPE | PR_SS
PLAN_END_DATE |  | SQLITE | PRIMAVERA |  |  | ACT_WORK_QTY | 290 | Actual Units | 290 | estimate at completion - labor units |  | Actual Units | TARGET_QTY | 302.4 | Planned Units | 302.4 |  | ACT_EQUIP_COST | 0
|  | SUMTASKSPREAD | ATIVIDADES NO TEMPO |  |  | TARGET_WORK_QTY | 302.4 | Planned Units | 302.4 | planne value labor units | earned vlue labor units | planned units | ACT_REG_QTY | 290 | Actual Units | 290 |  | ACT_EQUIP_COST
|  | BCWP | EARNED VALUE COST | EARNED VALUE COST |  | TARGET_DRTN_HR_CNT | 302.4 |  |  | planne value labor units | earned vlue labor units |  | TARGET_COST | 21168 | Planned Cost | 21168 |  | ACT_EXPENSE_COST
|  | BCWS | PLANNED VALUE COST | PLANNED VALUE COST |  | REMAIN_WORK_QTY | 0 | [5 empty] | ACT_REG_COST | 20300 | Actual Cost | 20300 |  | BCWP | 12700.8
[6 empty] | TASK_TYPE | TT_Task | Activity Type | Task Dependent |  |  |  | ACT_OT_COST | 0 | Actual Overtime Cost | 0 |  | PERFM_WORK_QTY | 181.44
[6 empty] | DURATION_TYPE | DT_FixedDrtn | Duration Type | Fixed Duration and Units/Time |  |  |  | REMAIN_COST | 0 | Remaining Cost | 0 |  | BCWS | 11648
[6 empty] | STATUS_CODE | TK_Complete | Activity Status | Complete |  |  |  | ACT_START_DATE | 40515 | Actual Start | 40880 |  | SCHED_WORK_QTY | 166.4
[6 empty] | TARGET_EQUIP_QTY | 0 | [5 empty] | ACT_END_DATE | 40567 | Actual Finish
[6 empty] | ACT_EQUIP_QTY | 0 | [5 empty] | TARGET_START_DATE | 40515 | Planned Start
[6 empty] | ACT_EQUIP_QTY | 0 | [5 empty] | TARGET_END_DATE | 40570 | Planned Finish
[6 empty] | ACT_START_DATE | 40515 | Actual Start | 40515 |  |  |  | RSRC_TYPE | RT_Labor | Resource Type | Labor
[6 empty] | ACT_END_DATE | 40567 | Actual Finish | 24/01/2011 A |  |  |  | RSRC_ID
[6 empty] | TARGET_START_DATE | 40515 | Start | 3/12/2010 A
[6 empty] | TARGET_END_DATE | 40570 | Finish | 40515
Mapeamento dos Campos
About XER Import/Export Data Map Guide (Resource Only)
https://docs.oracle.com/cd/F37128_01/English/Mapping_and_Schema/xer_import_export_data_map_resource_only/index.htm
| PROJ_ID | PROJECT ID | ACTIVITY ID |  | PROJ_ID | TASK_ID |  | WBS_ID |  |  |  |  | BASE_COST |  | PV COST NOV |  | BASE_WORK_COST |  |  | TARGET_WORK_QTY |  | Budgeted Labor Units | TOTAL_WORK_QTY
| 3878 | PROD00481 | PD9001 |  |  | 91874 |  | 23545 |  |  |  |  | 10657.5 |  | 10658 |  | 10657.5 |  |  | 108.75 |  | 108.75 | 108.75
|  | NRG00950 | A1040 |  | 4301 | 94252 |  | 24360
SUMTASKSPREAD
|  |  | ACT_COST |  | ACTUAL COST
START_DATE
END_DATE
SPREAD_TYPE
|  |  | BASE_COST |  | PLANNED VALUE COST
|  |  | BCWP |  | EARNED VALUE COST
|  |  | BCWS |  | PLANNED VALUE COST
EAC
ETC
About XER Import/Export Data Map Guide (Project)
https://docs.oracle.com/cd/F37128_01/English/Mapping_and_Schema/xer_import_export_data_map_project/helpmain.htm?toc.htm?97896.htm
Primavera Integration API Release
https://docs.oracle.com/cd/F37128_01/English/Integration/p6_pro_api_reference/index.html